## Log Issue (English)
Project name: เป๋าตัง หน้า G-Wallet | [6 empty] | Issue | High | Open | Pass | Done
Create by: Nuttapong Phetpradub | [6 empty] | CR | Medium | Doing | Pending | Re Open
Link : https://docs.google.com/presentation/d/1hkiEbsX2sBuMAs-cXLjYjdnoxsHRR8rGsHFbFzfDZ1k/edit?usp=sharing | [6 empty] | Bug | Low | Closed | New | Retest
Note
| No. | Module | Type | Data Test | Step | Description | Create Date | Priority | Status | Assign to | Closed Date | Remark
| 1 | Transfer Menu Page > Recipient Page > Transaction Page | Issue | PIN: 444444 Promptpay: 0123455155 | 1. Login 2. Click on the Money Transfer Button 3. Choose any Recipient's Account | Please change the Display format of the First and Lastname section as per below: Firstname Lastname displayed only 2 alphabet Ex. Nuttawan He | 2023-03-23 | Medium | New | Pannarai
| 2 | Transfer Menu Page > Recipient Page > Transaction Page > Transfer Confirmation Page | Bug | PIN: 444444 Promptpay: 0123455155 Amount of Money: 15 บาท Amount of Money: 50001 บาท | 1. Login 2. Click on the Money Transfer Button 3. Choose any Recipient's Account 4. Input the Amount of Money 5. Click Confirm Button | Please change the Display format of the amount of money section to two decimals as per below: Ex. 15.00 THB | 2023-03-23 | High | New | Pannarai
| 3 | Transfer Menu Page > Recipient Page > Transaction Page > Transfer Confirmation Page | Bug | PIN: 444444 Promptpay: 0123455155 Amount of Money: 15 บาท Amount of Money: 50001 บาท | 1. Login 2. Click on the Money Transfer Button 3. Choose any Recipient's Account 4. Input the Amount of Money 5. Click Confirm Button | Please change the Display format of the fee section as per these conditions: 1. When input amount of money between 0 - 50,000 THB; (Add. Fee 20 THB) 2. When input amount of money between 50,000 THB; (Add. Fee 50 THB) | 2023-03-23 | High | New | Cruella
| 4 | Transfer Menu Page > Recipient Page > Transaction Page > Transfer Confirmation Page > PIN Confirmation Page | Issue | PIN: 444444 Promptpay: 0123455155 Amount of Money: 15 บาท Amount of Money: 50001 บาท | 1. Login 2. Click on the Money Transfer Button 3. Choose any Recipient's Account 4. Input the Amount of Money 5. Click Confirm Button | Please change the Display format of the Wallet money and amount of money section as per these conditions: Font size and number: Money in wallet 15.50 THB. Increase the size by 1.125 times from the root's original size. | 2023-03-23 | Low | New | Cruella
| 5 | Transfer Menu Page > Recipient Page > Transaction Page | Issue | PIN: 444444 | 1. Login 2. Click on the Money Transfer Button 3. Choose any Recipient's Account | Please change the Display format of the Bank Section as per these conditions: 1. For Thai Accounts > Display only Krungthai Bank icon with its name 2. For Chinese Accounts > Display only Kasikorn Bank icon and Krungthep with their names | 2023-03-23 | High | New | Cruella
| 6 | Transfer Menu Page > Recipient Page > Transaction Page > Transfer Confirmation Page > PIN Confirmation Page | Bug | PIN: 444444 | 1. Login 2. Click on the Money Transfer Button 3. Choose any Recipient's Account 4. Input the Amount of Money 5. Click Confirm Button | Please modify the page to display the keyboard on the PIN input screen. (As current, the keyboard layout won't pop up) | 2023-03-23 | High | New | Shawn
| 7 | Add Credit/Debit Card Page | Bug | PIN: 444444 Click on the Credit/Debit Button Expiration Date (mm/yy): 99/99 | 1. Login 2. Click on Add the Credit/Debit Card | On the Add the Credit/Debit Card Page, please examine and fix why the month text field in the expiry date (month/year) field section can be input with a 99 number. | 2023-03-23 | Medium | New | Shawn
| 8 | Add Credit/Debit Card Page | Bug | PIN: 444444 Click on the Credit/Debit Button Expiry Date (mm/yy): 99/99 | 1. Login 2. Click on Add the Credit/Debit Card | On the Add the Credit/Debit Card Page, the number of digits for the year in the expiry date (month/year) field should be displayed as YYYY. | 2023-03-23 | Medium | New | Shawn
| 9 | Add Credit/Debit Card Page | Bug | PIN: 444444 Click on the Credit/Debit Button CVV: 123 | 1. Login 2. Click on Add the Credit/Debit Card | On the Add Credit/Debit Card page, Please make the necessary changes to display the keyboard when filling out the CVV text field. | 2023-03-23 | High | New | Shawn
| 10 | Home Page | Issue | PIN: 444444 | 1. Login | On Home Page, สิทธิ์คนละครึ่ง Banner should be removed from the page. | 2023-03-23 | Medium | New | Mariah
| 11 | Home Page | Bug | PIN: 444444 Click on the Statement Button | 1. Login | On Home Page, the Statement button doesn't respond to any click attempts. Please, fix it. | 2023-03-23 | High | New | Mariah
| 12 | PIN Identification Page | CR |  |  | When opening the application, on PIN Identification Page, please add another login alternative with Google Mail Login | 2023-03-23 | High | New | Mariah |  | Users require the case will be completed before the next UAT on 29/03/23
| 13 | Settings Page | Issue | PIN: 444444 | 1. Login 2. Click on Settings Button | On Settings Page, Please remove Sign out Button | 2023-03-23 | Medium | New | Zeus
| 14 | Settings Page | Bug | PIN: 444444 | 1. Login 2. Click on Settings Button | Please change the current format of the application version to this format: dd.YYYY.running001-999 เช่น 05.2021.001 | 2023-03-23 | Medium | New | Zeus

## Log Issue G-wallet
Project name: เป๋าตัง หน้า G-Wallet | [5 empty] | Issue | High | Open | Pass | Done
Create by: | [5 empty] | CR | Medium | Doing | Pending | Re Open
Link : https://docs.google.com/presentation/d/1hkiEbsX2sBuMAs-cXLjYjdnoxsHRR8rGsHFbFzfDZ1k/edit?usp=sharing | [5 empty] | Bug | Low | Closed | New | Retest
Note
No. | Module | Type | Data Test | Step | Description | Create Date | Priority | Status | Assign to | Closed Date | Remark
1 | เมนูโอนเงิน > หน้าจอบัญชีปลายทางการโอน > หน้าจอระบุจำนวนเงิน | Issue | PIN: 444444 Promptpay: 0123455155 | 1. ล็อกอิน 2. เลือกเมนูโอนเงิน 3. เลือกบัญชีปลายทางการโอน | เปลี่ยนรูปแบบการแสดงข้อมูลชื่อและนามสกุลดังนี้: ชื่อจริง นามสกุลแสดงเพียง 2 ตัวอักษร เช่น ณฐวรรณ์ เห | 2023-03-23 | Medium | New | Pannarai
2 | เมนูโอนเงิน > หน้าจอบัญชีปลายทางการโอน > หน้าจอระบุจำนวนเงิน > หน้าจอยืนยันการโอนเงิน | Bug | PIN: 444444 Promptpay: 0123455155 จำนวนเงิน: 15 บาท จำนวนเงิน: 50001 บาท | 1. ล็อกอิน 2. เลือกเมนูโอนเงิน 3. เลือกบัญชีปลายทางการโอน 4. พิมพ์จำนวนเงิน 5. กดปุ่มยืนยัน | เปลี่ยนรูปแบบการแสดงข้อมูลจำนวนเงิน ให้เป็นทศนิยม 2 ตำแหน่งตามนี้: เช่น 15.00 บาท | 2023-03-23 | High | New | Pannarai
3 | เมนูโอนเงิน > หน้าจอบัญชีปลายทางการโอน > หน้าจอระบุจำนวนเงิน > หน้าจอยืนยันการโอนเงิน | Bug | PIN: 444444 Promptpay: 0123455155 จำนวนเงิน: 15 บาท จำนวนเงิน: 50001 บาท | 1. ล็อกอิน 2. เลือกเมนูโอนเงิน 3. เลือกบัญชีปลายทางการโอน 4. พิมพ์จำนวนเงิน 5. กดปุ่มยืนยัน | เปลี่ยนรูปแบบการแสดงผลข้อมูลค่าธรรมเนียมตามเงื่อนไขนี้: 1. เมื่อกรอกจำนวนเงินตั้งแต่ 0 - 50,000 THB; (ค่าธรรมเนียม 20 บาท) 2. เมื่อกรอกจำนวนเงินตั้งแต่ 50,000 THB ขึ้นไป; (ค่าธรรมเนียม 50 บาท) | 2023-03-23 | High | New | Cruella
4 | เมนูโอนเงิน > หน้าจอบัญชีปลายทางการโอน > หน้าจอระบุจำนวนเงิน > หน้าจอยืนยันการโอนเงิน > หน้าจอการใส่ PIN | Issue | PIN: 444444 Promptpay: 0123455155 จำนวนเงิน: 15 บาท จำนวนเงิน: 50001 บาท | 1. ล็อกอิน 2. เลือกเมนูโอนเงิน 3. เลือกบัญชีปลายทางการโอน 4. พิมพ์จำนวนเงิน 5. กดปุ่มยืนยัน | เปลี่ยนรูปแบบการแสดงผลของเงินในวอลเล็ตและจำนวนเงินตามนี้: ขนาดตัวอักษรและตัวเลข: เงินในวอลเล็ต 15.50 บาท ให้ใหญ่ขึ้นจากเดิม 1.125 เท่าจาก root | 2023-03-23 | Low | New | Cruella
5 | เมนูโอนเงิน > หน้าจอบัญชีปลายทางการโอน > หน้าจอระบุจำนวนเงิน | Issue | PIN: 444444 | 1. ล็อกอิน 2. เลือกเมนูโอนเงิน 3. เลือกบัญชีปลายทางการโอน | เปลี่ยนรูปแบบการแสดงผลตรงส่วนธนาคารตามเงื่อนไขดังนี้: 1. คนไทย > ให้แสดงผลธนาคารกรุงไทยกับชื่อ 2. คนจีน > แสดงผลแค่ธนาคารกสิกรกับกรุงเทพกับชื่อ | 2023-03-23 | High | New | Cruella
6 | เมนูโอนเงิน > หน้าจอบัญชีปลายทางการโอน > หน้าจอระบุจำนวนเงิน > หน้าจอยืนยันการโอนเงิน > หน้าจอการใส่ PIN | Bug | PIN: 444444 | 1. ล็อกอิน 2. เลือกเมนูโอนเงิน 3. เลือกบัญชีปลายทางการโอน 4. พิมพ์จำนวนเงิน 5. กดปุ่มยืนยัน | แก้ไขให้แป้นพิมพ์แสดงผลในหน้าจอการใส่ PIN | 2023-03-23 | High | New | Shawn
7 | เมนูเพิ่มบัตรเครดิต/เดบิต | Bug | PIN: 444444 กดปุ่มเมนูเพิ่มบัตรเครดิต/เดบิต | 1. ล็อกอิน 2. ปุ่มเพิ่มบัตรเครดิต/เดบิต | ในหน้าจอเพิ่มบัตรเครดิต/เดบิต ตรวจสอบว่าทำไมถึงกรอกช่องเดือนด้วยตัวเลข 99 ได้ ในส่วนวันหมดอายุ (เดือน/ปี) | 2023-03-23 | Medium | New | Shawn
8 | เมนูเพิ่มบัตรเครดิต/เดบิต | Bug | PIN: 444444 กดปุ่มเมนูเพิ่มบัตรเครดิต/เดบิต วันหมดอายุ (ดด/ปป): 99/99 | 1. ล็อกอิน 2. ปุ่มเพิ่มบัตรเครดิต/เดบิต | บนหน้าจอเพิ่มบัตรเครดิต/เดบิต ในส่วนวันหมดอายุ (เดือน/ปี) จำนวนหลักของปีควรแสดงผลเป็น: YYYY | 2023-03-23 | Medium | New | Shawn
9 | เมนูเพิ่มบัตรเครดิต/เดบิต | Bug | PIN: 444444 กดปุ่มเมนูเพิ่มบัตรเครดิต/เดบิต CVV: 123 | 1. ล็อกอิน 2. ปุ่มเพิ่มบัตรเครดิต/เดบิต | ในหน้าจอเพิ่มบัตรเครดิต/เดบิต แก้ไขให้แป้นพิมพ์แสดงผล เมื่อจะกรอก CVV text field | 2023-03-23 | High | New | Shawn
10 | Home Page | Issue | PIN: 444444 | 1. ล็อกอิน | Home Page > แบนเนอร์สิทธิ์คนละครึ่ง รบกวนตัดส่วนนี้ออกไปไม่ให้แสดงผลในหน้าจอ | 2023-03-23 | Medium | New | Mariah
11 | Home Page | Bug | PIN: 444444 | 1. ล็อกอิน | ในหน้า Home > ปุ่มรายการย้อนหลังไม่ตอบสนองต่อการคลิกรบกวนแก้ไข | 2023-03-23 | High | New | Mariah
12 | หน้า - ระบุ PIN | CR |  |  | เปลี่ยนการแสดงผลข้อมูลโดยการเพิ่มวิธีการ Login ผ่านไลน์และGoogle Mail ในหน้า - ระบุ PIN หน้าแรกเมื่อเปิดแอพ | 2023-03-23 | High | New | Mariah |  | อยากให้ทัน UAT วันพุธที่ 29/03/23
13 | หน้าจอตั้งค่าการใช้งาน | Issue | PIN: 444444 | 1. ล็อกอิน 2. คลิกที่ปุ่มตั้งค่าการใช้งาน | ลบ ปุ่มออกจากระบบ ออกจากหน้าจอตั้งค่าการใช้งาน | 2023-03-23 | Medium | New | Zeus
14 | หน้าจอตั้งค่าการใช้งาน | Bug | PIN: 444444 | 1. ล็อกอิน 2. คลิกที่ปุ่มตั้งค่าการใช้งาน | เปลี่ยนรูปแบบการแสดงผลของเวอร์ชั่น ให้เป็นรูปแบบนี้: dd.YYYY.running001-999 เช่น 05.2021.001 | 2023-03-23 | Medium | New | Zeus